## Sayfa1
|  | 30.09.2024-6.10.2024 | 07.10.2024-13.10.2024 | 14.10.2024-20.10.2024 | 21.10.2024-27.10.2024 | 28.10.2024-03.11.2024 | 04.11.2024-10.11.2024 | 11.11.2024-17.11.2024 | 18.11.2024-24.11.2024 | 25.11.2024-01.12.2024 | 02.12.2024-08.12.2024 | 09.12.2024-15.12.2024 | 16.12.2024-22.12.2024 | 23.12.2024-29.12.2024 | 30.12.2024-05.01.2025
Start Date: 30.09.2024 |  | WEEK 1 | WEEK 2 | WEEK3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14
Preparing | week(1-3)
Project Searching | team | bar: WEEK 1
Project Propasal | can mete | bar: WEEK 2 to WEEK3
Project Selection | can mete | bar: WEEK 2 to WEEK3
Project plan | week(4-6)
Literature Review | kıvılcım | bar: WEEK 4 to WEEK 5
Discuss with Business Expert | team | bar: WEEK 5 to WEEK 6
Determine Context Boundries | eray | bar: WEEK 6
Determine Events in the system | sarper | bar: WEEK 6
Architecture | week(7-10)
Designing Software Architecture | team | bar: WEEK 7 to WEEK 10
Designing Infrastructure | team | bar: WEEK 7 to WEEK 10
Documentation | week(9-14)
Software Requirements Specification | team | bar: WEEK 9 to WEEK 11
Web Page | sarper,eray | bar: WEEK 9 to WEEK 11
Software Design Description | kıvılcım, can mete | bar: WEEK 11 to WEEK 13
Project Report | team | bar: WEEK 12 to WEEK 14
Presentation | week 14
Presentation | team | bar: WEEK 14